## AY18-19 Project Timeline
KAPIOLANI COMMUNITY COLLEGE
ACTIVE CAPITAL PROJECTS
Project Nane | Construction, Design, Assessment | 2018-06-29 | 2018-07-13 | 2018-07-27 | 2018-08-10 | 2018-08-24 | 2018-09-07 | 2018-09-21 | 2018-10-05 | 2018-10-19 | 2018-11-02 | 2018-11-16 | 2018-11-30 | 2018-12-14 | 2018-12-28 | 2019-01-11 | 2019-01-25 | 2019-02-08 | 2019-02-22 | 2019-03-08 | 2019-03-22 | 2019-04-05 | 2019-04-19 | 2019-05-03 | 2019-05-17 | 2019-05-31 | 2019-06-14 | 2019-06-28 | 2019-07-12 | 2019-07-26 | 2019-08-09 | 2019-08-23 | 2019-09-06 | 2019-09-20 | 2019-10-04 | 2019-10-18 | 2019-11-01 | 2019-11-15 | 2019-11-29 | 2019-12-13 | 2019-12-27 | 2020-01-10 | 2020-01-24 | 2020-02-07 | 2020-02-21 | 2020-03-06 | 2020-03-20 | 2020-04-03 | 2020-04-17 | 2020-05-01 | 2020-05-15 | 2020-05-29 | 2020-06-12 | 2020-06-26 | 2020-07-10 | Notes | Impact to Campus
Mokihana Renovation for Student Success Phase 1 | C | [55 empty] | Noise
KCC, Upgrade Campus Switchgear Phase I | C | [54 empty] | Began July 2017 | N/A
University of Hawaii Community Colleges System Wide Accessibility Assessment | A | [55 empty] | N/A
Kokio Building Assessment | A | [55 empty] | N/A
Naio Interior Renovation | C | [54 empty] | Began 6/12/18 projected comp date 12/2019 | Noise, Relocation of services, Relocation of staff
6928 Ohia Renovate Cafeteria and 6930 & 6928 Ohia Replace Kitchen Flooring | C | [55 empty] | Noise, Closure, Service Disruption
Culinary Institue of the Pacific (Phase II DESIGN/BUILD) | D, C | [54 empty] | Relocation | Fiscal
Manono, Title III Kauhale Ke Kuleana Renovation for Student Success | D, C | [55 empty] | Noise, Relocation of services, Relocation of staff
Olapa Re-Roof | D, C | [55 empty] | Noise
Ohelo Replace A/C (PENDING LEGISLATIVE R&M/MCIP APPROPRIATION) | D | [55 empty] | Noise
Title III Part F final project of this cycle | D, C | [55 empty] | U/K
Upper Campus Repair/Resurface Exterior Concrete Stairway Spalling | C | [55 empty] | N/A
6918 Mokihana, 6916 Maile, 6917 Mamane Repair Portables, Phase 1 | C | [54 empty] | Phase 1 of 3 phases | Noise, Relocation of services, Relocation of staff
Parking Lot C: Repair and Resurface Parking Lot | C | [54 empty] | Currentlyin Design | Loss of Parking temporarily
Kokio Various Repairs (PENDING LEGISLATIVE LINE ITEM APPROPRIATION!) | D, C | [54 empty] | Construction to begin no earlier than August 2020 | Noise, Relocation of Classes, Relocation of services, Relocation of staff
CC Energy Efficiency Phase II (SEE NOTES) | D, C | [54 empty] | Window Film (Complete), Transformers (Complete 8/15/2018), Lighting (7/2/2018-11/15/18), Solar (5/1/19-1/1/2020) | Noise, Brief office interruptions